| USER | : | INPEX Operation Pty Ltd. |
| --- | --- | --- |
| CLIENT | : | INPEX Operation Pty Ltd. |
| PROJECT | : | Ichthys Gas Field Development, ICSS ITT |
| DOC. NO. | : | C810-AJ-PLN-0001 (IGFDP-C0-PC-00-0100-001) |
| Cat. | : | ICSS ITT |

ICSS Project Execution Plan

| Rev. No. | Revision Description | Date of Issue dd-mmm-yy | Originator | Reviewed By | Approved By |
| --- | --- | --- | --- | --- | --- |
| D0 | For review | 06-Nov-09 | DK | DK | PM |
| D1 | Updated with Company reviewed comments | 12-Apr-10 | DK | PS | PM |
| D2 | Updated with Company reviewed comments (revD1/B) | 11-Oct-10 | DK | PS | PM |
| D3 | Issued for ICSS ITT | 26-Oct-11 | CC | SL | PM |
| D4 | Issued for Onshore ITT | 09-Nov-2011 | CC | SL | PM |

| Total No. of pages of this document (cover page) | [68] |  |
| --- | --- | --- |
| Total No. of pages of Attachment-01 (including cover page) | [03] |  |
| Total No. of pages of Attachment-02 (including cover page) | [14] |  |
| Total No. of pages of Attachment-03 (including cover page) | [13] |  |
| Total No. of pages of Attachment-04 (including cover page) | [10] |  |
| Total No. of pages of Attachment-05 (including cover page) | [19] |  |
| Total No. of pages of Attachment-06 (including cover page) | [02] |  |
| Total No. of pages of Attachment-07 (including cover page) | [12] |  |
| Total No. of pages of Attachment-08 (including cover page) | [14] |  |
| Total No. of pages of Attachment-09 (including cover page) | [05] |  |
| Total No. of pages of Attachment-10 (including cover page) | [03] |  |
| Total No. of pages of Attachment-11 (including cover page) | [04] |  |
| Total No. of pages (including cover page) | [167] |  |

REVISION HISTORY

| Date dd-Mmm-yy | Rev. | By | Description |
| --- | --- | --- | --- |
| 06-Nov-09 | D0 | DK | For Company Review |
| 12-Apr-10 | D1 | DK | Updated with Company reviewed comments (revD0) |
| 11-Oct-10 | D2 | PM | Updated with Company reviewed comments (revD1/B) |
| 26-Oct-11 | D3 | PM | Issued for ICSS ITT |
| 09-Nov-11 | D4 | PM | Issued for ICSS ITT (Onshore) |

TABLE OF CONTENT

1	Introduction	6

1.1	Purpose of this document	6

1.2	How This Document Organised	6

1.3	Acronyms and Abbreviations	7

1.4	References	11

1.5	ICSS Overall Organisation Strategy during Project Execution Phase	12

1.6	Owner (INPEX Operation Pty Ltd)	12

1.7	EPC Contractors	13

2	ICSS Supplier Project Scope of Work	14

2.1	ICSS Package Scope of Work – By ICSS Supplier	14

2.2	ICSS Supplier Project Development Cycle	15

2.3	ICSS Project Execution Flowchart	23

2.4	Major Milestones	25

3	Quality Control, Health Safety & Environment	27

3.1	ICSS Supplier Project Quality Plan	27

3.2	Sub-Vendors Quality Control	27

3.3	Health Safety and Environment (HSE)	27

3.4	ICSS Supplier HSE Risk Management	28

3.5	ICSS Supplier HSE Employee Handbook	29

3.6	ICSS Supplier HSE Implementation	29

3.7	ICSS Supplier HSE Monitoring	29

4	ICSS Supplier Project Execution and Organisation	30

4.1	ICSS Project Organisation	30

5	Communication Procedures	40

5.1	Internal Project Meetings	40

5.2	Technical Meetings	40

5.3	Monthly Progress Meetings	40

5.4	ICSS Supplier Project Reviews, Basic Design Review (i.e. Hardware Freeze), Detail Design Review (i.e. Software Freeze) and System Readiness Review (SRR)	41

6	Procurement Management	43

6.1	Responsibility	43

6.2	Uniform Hardware	43

6.3	ICSS Hardware	43

6.4	SIS/FGS/HIPS/AFS (HIMA)	43

6.5	Other Packages	43

6.6	Expediting	44

7	Technical clarification	45

7.1	Technical Clarification Procedure	45

8	ICSS Change Management	46

8.1	Change Request Procedure	46

8.2	Change Management Process	46

9	Document Handling	48

9.1	ICSS Supplier FEED/PRE-FID and Project Documents relationship	48

9.2	Document Server, Software Platform & Applications	50

9.3	Document Controller	50

9.4	ICSS Project Documents	50

9.5	Document Approval	52

9.6	Document Format	53

9.7	Document Structure	53

9.8	Document Numbering Philosophy	54

9.9	EPC Phase Standard Document Requirements (ICSS and PCS Document Title and Number)	55

9.10	Revision Control	58

9.11	Review on Engineering Document	59

9.12	As-Shipped Documents	59

9.13	Update of Document at EPC Contractor’s Plant Site	60

10	Correspondence	61

10.1	Correspondence References	61

11	ICSS Supplier Project Document Templates	66

11.1	The project document templates	66

11.2	EPC Contractor/Company coversheet	66

12	Disaster Recovery	67

12.1	Recovery Responsibilities	67

12.2	Recovery Overview	67

12.3	Recovery Procedure	67

| Attach-ment |  | Attachment Document Number | Attachment Document Title |
| --- | --- | --- | --- |
| -01 | C8190AJ-PLN-0001 (IGFDP-C0-PC-00-0100-001-01RevD3) |  | ICSS Project Organisation Chart |
| -02 | C8190AJ-PLN-0001 (IGFDP-C0-PC-00-0100-001-02_revD3) |  | ICSS Technical Clarification Procedure |
| -03 | C8190AJ-PLN-0001 (IGFDP-C0-PC-00-0100-001-03_revD3) |  | ICSS Change Request Procedure |
| -04 | C8190AJ-PLN-0001 (IGFDP-C0-PC-00-0100-001-04_revD3) |  | ICSS Document Numbering Philosophy |
| -05 | C8190AJ-PLN-0001 (IGFDP-C0-PC-00-0100-001-05_revD3) |  | ICSS Document Template |
| -06 | C8190AJ-PLN-0001 (IGFDP-C0-PC-00-0100-001-06_revD3) |  | Non-Material Requirements (ICSS Document Title and Number |
| -07 | C8190AJ-PLN-0001 (IGFDP-C0-PC-00-0100-001-07_revD3) |  | ICSS System Log Form Event/Report Procedure |
| -08 | C8190AJ-PLN-0001 (IGFDP-C0-PC-00-0100-001-08_revD3) |  | ICSS Change Order Procedure |
| -09 | C8190AJ-PLN-0001 (IGFDP-C0-PC-00-0100-001-09_revD3) |  | ICSS Progress report Template |
| -10 | C8190AJ-PLN-0001 (IGFDP-C0-PC-00-0100-001-10_revD3) |  | COMPANY Cover-page Template for ICSS Doc. |
| -11 | C8190AJ-PLN-0001 (IGFDP-C0-PC-00-0100-001-11_revD3) |  | ICSS Inputs from EPC Contractor |

# Introduction

## Purpose of this document

This ICSS Supplier Project Execution Plan (PEP) defines the procedures, project management methods and guide lines which shall be used by ICSS Supplier to manage IGFDP ICSS Projects during EPC Phases.  ICSS Supplier is the ICSS supplier for this facility, which includes PCS and other systems. 
This document does not cover the ICSS FEED; refer to FEED execution plan (FEP).

## How This Document Organised

This document is organised as follows:

Section 1 – Introduction – it provide an outline of this document, acronyms and abbreviations used within this document and the scope.

Section 2 - Defines briefly the scope of work for ICSS and its related interfaces, responsibility matrix in the project.

Section 3 - Quality Control, Health Safety & Environment - provides details on quality control in various areas.  It covers on health, safety and environment issues to ensure a safety and commitment to friendly environment.

Section 4 - ICSS Supplier Project Execution and Organisation - describes the project typical organisation and responsibilities and function of each project member.

Section 5 - Communication Procedures - defines communication in the project.  How technical and management meetings to be conducted, as well as correspondence, and reviews such as    Design review, Functional design review, System Readiness Review etc.

Section 6 - Procurement Management - covers the procurement management to ensure uniform hardware being used throughout the project.

Section 7 –– provides the Technical Clarification Notice Procedure (TCN) on how address technical related issues through the use of Technical Clarification Notice (TCN).

Section 8 –– provides the Change Request Procedure (CRP) on how change requests from EPC CONTRACTOR to be reviewed and handled.  A Change Request Form (CRF) is attached to the procedure.

Section 9 – Document Handling - defines how documents are handled.  Non-Material Requirements (ICSS and PCS Document Title and Number) has been provided as an attachment to this document.  ICSS Numbering Philosophy attached to this document, details how document number can be assigned.  Document formats and revision control are discussed.

Section 10 – Correspondence - defines how correspondence are handled and the formats used.  Both incoming and outgoing correspondences are tracked.

Section 11 – ICSS Supplier Project Document Templates - defines how document template for main document and attachment cover sheet should be used for standardisation and uniformity in presentation.

Section 12 – Disaster Recovery - defines how document and correspondence are handled.  Document formats and revision control are discussed.

## Acronyms and Abbreviations

All acronyms and abbreviations used in the document are listed below:

| ADAS | Analyser Data Acquisition System |
| --- | --- |
| ALMS | Alarm Management System |
| AMS | Asset Management System |
| APC | Advance Process Control |
| AS | Analyser Shelter |
| AS | Australian Standards |
| BCS | Ballast Control System |
| BMS | Burner Management System |
| CAD | Computer Aided Design |
| CA-PA | Corrective Action - Preventive Actions |
| CAR | Corrective Action Request |
| CCB | Central Control Building |
| CCR | Central Control Room |
| CCS | Compressor Control System |
| CCTV | Closed Circuit Television System |
| CD-ROM | Compact Disc Read-Only Memory |
| CHAZOP | Computer Hazardous and Operability Study |
| CMS | Condition Monitoring System |
| COF | Change Order Form |
| COP | Change Order Procedure |
| CPF | (Offshore) Central Processing Facility |
| CRF | Change Request Form |
| CRP | Change Request Procedure |
| DB | Database |
| DC | Drilling Centre |
| DCC/DC | Document Controller |
| DCS | Distributed Control System (same as PCS) |
| DDS | Detail Design Specification |
| DM | Department Manager (ICSS Supplier) |
| DMZ | Demilitarized Zone |
| DN | Delivery Notice |
| DO | Delivery Order |
| EM | Engineering Manager (ICSS Supplier) |
| EMC | Electromagnetic Compatibility |
| EPC | Engineering Procurement & Construction |
| ESD | Emergency Shutdown System |
| ExaOPC | Yokogawa OPC Server |
| FAT | Factory Acceptance Test |
| FCS | Field Control Station (PCS controller) |
| FDS | Functional Design Specification |
| FEED | Front End Engineering |
| FEP | Feed Execution Plan |
| FGS | Fire and Gas System |
| FLD | Fault Logic Diagram |
| FO | Fibre Optic |
| FOB | Free On Board milestone |
| FOC | Fibre Optic Communication/Cabinet |
| FPSO | (Offshore) Floating, Production, Storage and Offloading |
| GCP | Generator Control Panel |
| GEP | Gas Export Pipeline |
| GPS | Global Positioning System |
| GTCS | Gas Turbine Control System |
| GW | Gateway |
| HART | Highway Addressable Remote Transducer |
| HIPS | High Integrity Protection System |
| HIS | Human Interface Station/Operator |
| HIS-ENG | Human Interface Station/Engineering |
| HMI | Human Machine Interface |
| HSE | Human Safety and Environment |
| HVAC | Heat, Ventilation, and Air Conditioning |
| HW | Hardware |
| HWF | Hardware Freeze Milestone (Basic Design) |
| I/O, IO | Input / Output |
| ICSS | Integrated Control and Safety System |
| ICT | ICSS Core Team (ICSS Supplier) |
| IEC | International Electro technical Committee |
| IER | Instrument Equipment Room |
| IFAT | Integrated Factory Acceptance Test |
| IGFDP | Ichthys Gas Field Development Project |
| IPT | ICSS Project Team (EPC Phase) |
| ISO | International Organization for Standardization |
| IT | Information Technology |
| ITT | Invitation To Tender |
| JKC | JGC/KBR/CHIYODA Joint Venture |
| KO | Kick Off |
| KOM | Kick-Off Meeting |
| LAN | Local Area Network |
| LCS | Local Control Station |
| LDS | Laboratory Data System |
| LER | Local Electrical Room |
| LIR | Local Instrument Room |
| LNG | Liquefied Natural Gas |
| LOI | Letter Of Intent |
| LPE | Lead Project Engineer (PEP) |
| LPG | Liquefied Petroleum Gas |
| LSE | Lead System Engineer |
| MCC | Motor Control Centre |
| MEG | Mono Ethylene Glycol |
| MMS | Machine Monitoring System |
| MOM | Minutes Of Meeting |
| MPUS | Mechanical Package Unit Control & Monitoring System |
| MRD | Mobile Reference System |
| MS | Microsoft |
| NC | Non Conformance |
| NCR | Non Conformity Report |
| NT | Northern Territory (AUS) |
| ODS/ODSS | Operator Decision Support System |
| OLE | Object Linking and Embedding |
| OPC | OLE for Process Control |
| OTS | Operator Training System |
| P&ID | Piping and Instrumentation Diagram |
| PCM | Project Control Manager |
| PCS | Process Control System |
| PD | Project Director |
| PDCS | Power Distribution Control System (Electrical) |
| PDP | Power Distribution Panel |
| PEP | Project Execution Plan |
| PER | Perth Engineering Office |
| PFD | Process Flow Diagram |
| PIN | Plant Information Network |
| PLC | Programmable Logic Controller |
| PLDS | Pipeline Leak Detection System |
| PLMS | Pipeline Management System |
| PM/PJM | Project Manager |
| PMD | Panel Manufacturing Department (ICSS Supplier) |
| PMS | Power Management System (Electrical) |
| PO | Purchase Order |
| PQP | Project Quality Plan |
| PRM | Plant Resource Management System (AMS) |
| PS | Project Support Staff ( PEP) |
| PSD | Process Shutdown System |
| PV | Package Vendor |
| QA | Quality Assurance |
| QC | Quality Control |
| QM | Quality Manager |
| QMS | Quality Management System |
| RFI | Radio Frequency Interface |
| RS | Reference System |
| RTDB | Real Time Database (Historian) |
| SAP | Enterprise Resource Planning (SW) |
| SAT | Site Acceptance Test |
| SCS | Subsea Control System |
| SE | System Engineer |
| SER | Sequence of Event Recorder System |
| SFC | Sequence Flow Chart |
| SIC | System Integration Centre (ICSS Supplier) |
| SIS | Safety Instrumented System |
| SOE | Sequence of Events |
| SOE/SER | Sequence of Event Recording |
| SOL | Solution Group (ICSS Supplier) |
| SOP | Standard Operating Procedure |
| SPS | Subsea Production System |
| SRR | System Readiness Review Milestone (PEP) |
| STCS | Steam Turbine Control System |
| SW | Software |
| SWF | Software Freeze milestone (Detail Design) |
| TBA/TBAL | To Be Advise Later |
| TCN | Technical Clarification Notice (PEP) |
| TCO | Total Cost of Ownership |
| TCP | Technical Clarification Procedure (PEP) |
| TGS | Tank Gauging System |
| TM | Technical Manager (PEP) |
| UCP | Unit Control Panel (Sub-System) |
| UPS | Uninterruptible Power Supply |
| VDPA | Volume Discount Price Agreement |
| VFAT | Vendor FAT |
| VMS | Vibration Monitoring System |
| Vnet/IP , Vnet | Yokogawa Process Control Network |
| WA | Western Australia (AUS) |
| YAS | Yokogawa Asia (Singapore Factory) |
| YAU | Yokogawa Australia Pte. Ltd. |
| YEA | Yokogawa Engineering Asia Pte. Ltd. |
| YHQ | Yokogawa Engineering Corporation (Japan) |

## References

This document is prepared with the reference to the following document(s):

| Doc.No. | Rev | Document Title |
| --- | --- | --- |
| C035-AG-SPC-0001 | C | Specification : Document & Drawing Submittals Requirements |
| C045-AG-PRC-0001 | 5 | Procedure :Project Document Numbering |
| C065-AG-SPC-0001 | 3 | Technical Change/Deviation Management Requirements |
| C065-AG-SPC-0002 | 4 | Specification : Project Control Requirements |
| C075-AH-SPC-0005 | 0 | Specification : Health, Safety and Environment – Performance reporting for Onshore Contract Requirements |
| C075-AH-SPC-0008 | 0 | Specification : Health, Safety and Environment – Offshore Contract Requirements |
| C075-AH-SPC-0004 | 5 | Specification : Health, Safety, Environment and Security Major Contract Onshore |
| C075-AQ-SPC-0004 | 1 | Specification : Quality Requirements for Contractors |
| C075-AQ-SPC-0001 | 1 | Specification : Quality Requirements for Suppliers |
| B810-AJ-SOW-0001 | 0 | CPF ICSS EXHIBIT A.1 SOW |
| B810-AJ-SOW-0002 | 1 | CPF/SPS Integration Pkg. ICSS EXHIBIT A.4 SOW |
| S810-AJ-SOW-0001 | 0 | FPSO ICSS EXHIBIT A.2 SOW |
| S810-AJ-SOW-0002 | 0 | FPSO Turret ICSS EXHIBIT A.5 SOW |
| L810-AJ-SOW-0001 | 0 | LNG ICSS EXHIBIT A.3 SOW |
| C810-AJ-SOW-0001 | 0 | Service to Company ICSS EXHIBIT A.0 SOW |

SEW-EM-301				Engineering Workflow

SEW-EM-701				DCS Application Software Backup and Disaster Recovery

SEW-EM-503				Project Document Practice

SEW-DC-101 				Document Control Procedure

SEW-F-601 				Procurement of Non-Yokogawa Products

SEW-F-603 				3rd Party Vendor Classification and Criteria for Evaluation

SEW-EM-362 				Project Identification and Traceability

| C810-AJ-LIS-0001 |  | ICSS FEED Master Document List |
| --- | --- | --- |
| C810-AJ-PLN-0002 |  | ICSS Project Quality Plan (PQP) |
| C810-DJ-SCM-0001 |  | ICSS System Architecture Schematic |
| C810-DJ-BLD-0001 |  | ICSS Overall Block Diagram |
| C810-AJ-SPC-0030 |  | ICSS Overview |
| C810-AJ-SPC-0021 |  | ICSS Network Specification |
| C810-AJ-SPC-0033 |  | EPC to ICSS Data Exchange Mechanism |

## ICSS Overall Organisation Strategy during Project Execution Phase

During the project execution phase (EPC Phase), ICSS Supplier shall form the ICSS project teams (IPTs), namely ICSS PT1, ICSS PT2, etc. corresponding to the each EPC contracted by COMPANY.  These ICSS project teams shall, base on EPC contract requirement interface with each EPC Contractor to carry out the respective scope of work.

There shall be also an ICSS Core team (ICT) directly contracted by Inpex for the ICSS overall coordination and engineering compliance roles.

Figure 1-1  ICSS Overall Organisation

## Owner (INPEX Operation Pty Ltd)

Company shall have an ICSS steering technical team representative in ICSS Supplier location (Singapore) throughout the entire ICSS development cycle till ICSS delivery.

## EPC Contractors

The following EPC Packages are currently anticipated for IGFDP Projects and related EPC Contractor name abbreviation for ICSS documentation:

| No | Location | Package | Package Abbreviation | ICSS Code | EPC Abbreviation | EPC Contractor | Eng. Location |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | ONSHORE | LNG Facilities | LNG | LN | JKC Note-1 | JKC | Japan |
| 2 | OFFSHORE | CPF | Top Side | BT | TBA | TBA | TBA |
|  |  |  | SPS Integr. | BS | TBA | TBA | TBA |
|  |  |  | Hull | BH | TBA | TBA | TBA |
| 3 |  | FPSO | Top Side | ST | TBA | TBA | TBA |
|  |  |  | Turret | SR | TBA | SBM | UK/MY |
|  |  |  | Hull | SH | TBA | TBA | TBA |
| 4 |  | Subsea Production System | SPS | US | TBA | TBA | TBA |

Note: This table is the register of the potential future ICSS Contracts, ICSS Code assigned here shall be used throughout ICSS documentation.

Note 1:	Joint Venture

Note 2:	TBA (To Be Advised); subject to change during PRE-FID/ ITT phases.

The Definitions used in this document are listed below:

Company	:  INPEX Operation Pty Ltd

EPC Contractor: Contractor responsible for the facility Engineering, Procurement and/or Construction.

# ICSS Supplier Project Scope of Work

## ICSS Package Scope of Work – By ICSS Supplier

The following are a brief description of ICSS packages to be included in the scope of work.

ICSS Supplier consists of main two major suppliers and manufacturer respectively:

- Yokogawa Australia (YAU), ICSS project execution is implemented by Yokogawa Engineering Asia Pte Ltd Singapore (YEA). YEA is the main automation supplier including services, equipment fabrication or material and responsible for the supply of services, equipment and material regarding the entire ICSS.

- Hima Australia Pty Ltd , project execution is implemented by HIMA Paul Hildebrandt GmbH + Co KG the supplier of services, equipment fabrication or material of all  Safety Systems and responsible for the supply of services, equipment and material regarding the Safety Systems (SIS,HIPS,FGS,AFS)

Yokogawa is the main ICSS supplier and Hima a sub-supplier of Yokogawa for all Safety Systems.

### ICSS Packages

The ICSS is segmented into multiple packages such as:

LNG facilities 					(800451-Onshore-LNG)

CPF 						(800449-Offshore-CPF)

SPS 						(800nnn-Offshore-SPS)

FPSO 						(800447-Offshore-FPSO)

FPSO Turret 					(800448-Offshore-FPSO-Turret)

Subsea to CPF to SPS Integration 		(800449-SPS/CPF Integration)

Inpex Operation Pty Ltd 			(800519-To Company)

### ICSS Scope of Work

Each ICSS Supplier’s IPT(s) scope of supplies is specified in:

Refer to B810-AJ-SOW-0001	CPF 				ICSS EXHIBIT A.1 SOW

Refer to B810-AJ-SOW-0002	CPF/SPS Integration Pkg. 	ICSS EXHIBIT A.4 SOW

Refer to S810-AJ-SOW-0001	FPSO 				ICSS EXHIBIT A.2 SOW

Refer to S810-AJ-SOW-0002	FPSO Turret 			ICSS EXHIBIT A.5 SOW

Refer to L810-AJ-SOW-0001	LNG  				ICSS EXHIBIT A.3 SOW

Refer to C810-AJ-SOW-0001 Services to Company 		ICSS EXHIBIT A.0 SOW

## ICSS Supplier Project Development Cycle

ICSS Supplier projects development cycle is divided into the following components:

Project Phases and Milestones

Project Work Package/Unit (within each phases)

### ICSS Project Development Phases and Milestones

ICSS projects Development cycle are essentially and primarily segmented by the following PHASES and Milestones (Fig 2-1). The ICSS Supplier Project Manager shall report the progress and quality gates for each phases and milestones in order to measure the project development status, risk area or critical milestone delays if any.

The ICSS Supplier Project Development cycle’s phases are implemented as followed:

Figure 2-1  ICSS Supplier Project Development Cycle

### ICSS Project Development Tasks and Work Packages

ICSS project’s multiple tasks and work breakdown are essentially decided and logically linked for each respective IPT including EPC Contractor’s project inputs, requirements and all ICSS material or non material deliverables that shall map to respective EPC Contractor’s development schedule.

WP01  Management Administration and Services

WP02  Health, Safety Environment and Security

WP03  Engineering

WP04  Procurement services

WP05  Fabrication and configuration

WP06  Testing

WP07  Packing, Loading, Transportation

WP08  Assistance during installation, pre-commissioning at EPC’s Fabrication Yard or Integration Yard

WP09  Assistance during commissioning, start-up and performance tests at final production Site (Onshore/Offshore)

WP10  Final documentation and information handover

WP11  Options

As this ICSS ITT SOWs for the EPC Phase are Ex Work (FOB) Singapore this PEP will exclude the detail ICSS execution of WP07, 08 and 09 that will be specified in an other specific site execution plan.

Refer to figure 2-3-2 below showing standard logical Project tasks and logical links not Project specific.

Figure 2-3-2 	ICSS Supplier Project typical tasks with essential finish to start links.

Note : Durations indicated are not the actual Project durations, refer to the actual L1 Project Schedule

### Design Validation by IPT

Besides the required project tasks, deliverables and schedule, the Company require to include the following dedicated tasks that shall be defined for each ICSS Projects:

Design and development validation Design shall be performed in accordance with planned arrangements as defined in the ICSS FEED/PRE-FID Standard Application specification to ensure that the resulting product is capable of meeting the requirements for the specified application or intended use. Wherever practicable, design validation test (DVT) shall be completed prior to the delivery or implementation of the product. Records of the results of validation and any necessary actions shall be maintained by both the ICT and IPTs.

Design validation includes one or more of the following:

prototype tests

functional and/or operational tests of Interface systems (3rd Party or UCPs)

tests specified by industry standards and/or regulatory requirements (DNV for Offshore Marine)

Hart field devices interoperability reviews

#### Hardware prototype or DVT

The hardware components and their installation in the ICSS equipments shall be demonstrated. Functionality of each individual major component shall be demonstrated and tested.

Cabinet prototype, it shall only cover type of cabinets not already done by the ICSS FEED/Pre-FID or not originally in the ICSS scope of supply.

Consoles of each type for Offshore and Onshore facilities.

#### Application Software Standard Applications DVT

The ICSS Standard Application were already pre-developed and tested as a part of the ICSS FEED/PRE-FID phases.

These test activities are reserved for new ICSS standard applications (or sub class of) specific to the current project requirement and not already functionally covered in the ICSS Standard Application register.

All project standard applications requirement shall be informed to the ICSS Core Team (ICT) Engineering Manager prior is initiation.

Refer to:

C810-AJ-PRC-0001 ICSS Standard Application Library Procedure

C810-AJ-DAT-0001 ICSS Standard Application Template Data Sheet

C810-AJ-LIS-0002 ICSS Standard Application Register

#### Application Software for 3rd party or UCP System DVT

ICSS prototype test (DVT) could be carried out for specific ICSS to 3rd Party/UCP System interface by respective project team using ICSS Mobile Reference Systems (MRS) as required.

The Project team shall also refer to the PCS – SIS/FGS/HIPS/3rd party communication specification which applies to each recognized different configurations as described in the ICSS Design Dossier Exhibit E documents such as C810-AJ-SPC-0018 (IFGDP-C0-PC-00-2800-001) ICSS Subsystems Communication Specification.

#### Validation test of EPC’s IO DB Table

Validation test of EPC specific IO DB exchange mechanism from the typical IO Data sample extracted by the EPC Contractor’s from the SPI DB.

#### HMI Design Validation

Prototype Test for HMI with validation by Company Operation as per the ISO Standard 13407:1999 Human Centred design process for interactive systems.

#### Prototype of HART® Field Instruments

Prototype of HART® Field Instruments with associated DD file for its interoperability with ICSS and PRM for required field devices specified or procured by EPC Contractor.

Refer to ICSS Test Plan C810-AJ-PLN-0004 for the Prototype or Test requirements.

| Prototyping responsibility Matrix |  |  |  |
| --- | --- | --- | --- |
| Category | Prototype testing | Typical change management | Remarks |
| Common Standard Applications applicable across all EPC | ICT | ICT |  |
| Additional Standard Applications applicable across all EPC (& Sub-Class) | IPT | ICT | Validation with ICT |
| EPC Project specific Applications & Typical | IPT | IPT | New or specific typical not in ICT list and unique to an EPC Design requirement |

### OTS specific milestones and inputs

OTS required EPC’s process facility and equipment design data availability for the simulator’s model implementation and validation such as : equipment datasheets,  device datasheets, control narratives, safety narratives, logic diagrams, PFD, P&ID,  material & heat balance, instrument datasheets and SOPs  for both process  and packages equipments.

For the Operation training purpose, the OTS shall be integrated with validated PCS & SIS control and safety database as per the ICSS FAT.

For Onshore LNG trains OTS including APC Operation training purpose, the OTS shall be integrated with a validated APC configuration database as per the APC FAT.

For the Offshore OTS including Subsea OTS Operation training purpose, the OTS shall be integrated with a validated OTS (by SPT) configuration database as per the OTS FAT.

OTS modelling shall be designed and validated by process engineering discipline, Process licensor(s) and Package supplier(s) as per EPC agreements.

Refer to figure 2-3-3 below showing typical OTS activities

Figure 2-3-3 Typical OTS Activities

### ICSS Project Development locations

## ICSS Project Execution Flowchart

### ICSS Project Execution Workflow

The typical ICSS flowchart show the logical and sequential interrelationships between the various project activities required to implement the project scope of work:

Figure 2-2  ICSS Supplier Project Execution Work Flow

The Company representative and EPC Contractor shall participate to the ICSS Supplier Kick-Off Meeting.

Figure 2-3  ICSS Supplier Project Execution Work Flow (cont'd)

## Major Milestones

MILESTONE

ICSS Supplier Project Kick-Off Meeting

Submit PEP/PQP

Submit ICSS Supplier L3 Project Schedule

Receipt of Design Inputs from EPC Contractor

ICSS FDS Submission to EPC Contractor for Basic Design

Basic Design Meeting

HW Prototyping

Hardware Freeze Milestone (HWF)

ICSS SW DDS Submission to EPC Contractor for Detail Design

Detail Design Review Meeting

SW Prototyping ( Typical loops, HMI ) , HART® FI Prototyping

Software Freeze Milestone (SWF)

Submit FAT Plan

Submit FAT Procedures

Implementation/Configuration Freeze

Conduct Internal Test (FIT)

SRR Audit

Factory Acceptance Test for all ICSS Systems (SIS, FGS, HIPS...etc)

Factory Acceptance Test for 3rd Party Systems (under EPC Contractor Scope)

Factory Acceptance Test for PCS

IFAT (Integration)

FAT Recovery & report book

Equipment ready for delivery (FOB, Singapore)

Final Documentation and submission

The dates for above milestones are to be agreed upon during the ICSS Supplier project KoM to form the basis of the specific EPC Contractor requirement and project schedule.

The active project target dates shall be referred to those in the related project schedule.

Note 1: Integration Testing occurs in a minimum of these steps:

Prototype – by ICSS Supplier, at Singapore office of ICSS

Prototype Validation - ICSS Supplier at premises of 3rd party to check new revisions and trial of data transfer after configuration and ahead of P3-Package Vendor FAT.

P3-Package Vendor FAT - ICSS Supplier at premises of 3rd party supplier testing interface before shipment from P3 Vendor Package.

Integrated Factory Internal Test - Package Vendors at the ICSS Supplier integrated FIT.

FAT - Customer witnessed ICSS integrated FAT

# Quality Control, Health Safety & Environment

## ICSS Supplier Project Quality Plan

ICSS Supplier is an ISO9001:2000 and ISO14000 certified company.  The company quality manual specifies the quality objective and companywide quality requirements.  Each individual department has job handling manuals and work standards to meet the company quality requirements.  Job handling manual SEW-JM-001 shall be used for project management and engineering quality control.

A detailed Project Quality Plan specify the ICSS Supplier Quality Management System

## Sub-Vendors Quality Control

The main sub-vendors shall be asked to submit their quality plan.  This shall be reviewed and approved by the ICSS Supplier Project & Engineering Manager to ensure that the sub-vendor quality plan meet or exceed the ICSS Supplier performance requirement. The ICSS Supplier Project Engineering Manager shall also periodically verify the quality performance of sub-vendors.

Refer to ICSS PQP; Doc No. C810-AJ-PLN-0002 for details of Sub-Vendor Quality tasks and evaluations.

## Health Safety and Environment (HSE)

Safeguarding environment and health is an international requirement.  At ICSS Supplier health, safety and environment is of the highest priority.  The company policy is to be “Environmentally Friendly”.

In the project, the implementation shall cover HSE as follows

HSE Management at project office area and its subcontractor’s office and staging area

EPC Contractor’s HSE at site

ICSS Supplier shall comply with both C075-AH-SPC-0004/8 COMPANY Project HSE requirements and ICSS Supplier requirements.

### ICSS Supplier HSE Management at Office

ICSS Supplier is an ISO14000 certified company and the policy on environment is “Be Environmentally Friendly”.  As part of the ISO14000 certification requirement, ICSS Supplier has established a company standard to be complied with by all personnel working in ICSS Supplier.  Targets are set for various activities that affect environment and are constantly monitored by company management representatives.  The company is also audited by an external auditor, Lloyd’s Register of Quality Assurance, for compliance to ISO14000 requirements.  In addition, ICSS Supplier complies with local statutory authority requirements on hazardous material handling, waste disposal etc.  Local authorities periodically inspect the company premises to verify compliance.

ICSS Supplier as a responsible company encourages all its vendors to adopt environmentally friendly methods to reduce the depletion of natural resources.

All temporary visitors to ICSS Supplier premises shall be accompanied by an ICSS Supplier staff at all times and visitors shall be guided in times of emergency.

All long time visitors shall be inducted with the HSE and security requirements to be complied with.  Emergency exits and assembly points are clearly identified.  Fire wardens shall guide all personnel to the assembly points and also take roll call at assembly point to ensure that all personnel have evacuated in case of emergency.

### ICSS Supplier Staging Area HSE

Following HSE requirements shall be enforced in staging area.

Adequate escape routes in the layout of equipment.

Fire fighting system.

Proper electrical protection for short circuit and overload to prevent fire and damage to equipment.

Protection against electrical shock.

Equipment power up and power down only by authorised ICSS Supplier staff.

Live warning signboards.

No food and drinks in the staging area.

No smoking in the staging area.

HSE guidelines hand-out to all personnel admitted in the staging area.

Access to only authorised personnel.

Only authorised personnel shall be allowed to work on the equipments.

Proper tools for working on the equipments.

A First Aid Box shall be provided in staging area.

### HSE at Site by COMPANY/EPC Contractors

ICSS Supplier Site scope and work are to be determined under the Site scope/work Purchase Order terms and Conditions.

All site, all Health, Safety and Environment issues shall be EPC Contractor’s responsibility and procedures.  EPC Contractor shall undertake the responsibility to ensure that all ICSS Supplier staff shall be aware of such requirements. ICSS Supplier staff shall abide by the requirements for any work involvement at site.

ICSS Supplier’s scope of site activities is primarily confined within the Control Centre and Process/Local Interface Buildings/Rooms and system commissioning and/or any locations where ICSS supplied equipments are located. The exposure to hazards and impact on environment from these activities is expected to be minimal.  However, as a responsible company ICSS Supplier considers Health, Safety and Environment aspects very seriously.  In view of this, ICSS Supplier ensures that all its site personnel are aware of the site HSE requirements whether it is directly relevant to their activities or not.

## ICSS Supplier HSE Risk Management

In our operations, HSE risks exist mainly at the project site.  These risks are managed by:

Safety Orientation Course to all site staff.

Safety Induction Course at site.

Providing copy of site HSE requirement.

Briefing by the team leader on work assignment, hazards and safety precautions prior to commencement of work.

Attending safety meetings conducted by project HSE manager.

Daily safety inspection.

Strict compliance to housekeeping.

Refresher course for safety violation.

Accident / Incident investigation and reporting.

Strict implementation of personal protective equipments required at the place of work.

Permit to work application where required.

Setting safety targets.

Incentive for exceeding safety targets.

## ICSS Supplier HSE Employee Handbook

ICSS Supplier has a company policy on HSE.  All ICSS Supplier personnel, visiting site is provided with a copy of this policy and must comply with it.  All staff posted at site is also required to comply with the specific HSE requirements of the site.

## ICSS Supplier HSE Implementation

HSE compliance is implemented by:

Site Manager’s emphasis on safety policy.

Assigning responsibility to various levels of site staff.

Pre-start meetings.

Monthly meetings.

Ad-hoc meetings.

On site meetings and instructions.

Regular inspections.

## ICSS Supplier HSE Monitoring

HSE monitoring is carried out by:

Walk around by site manager.

Safety inspection by safety supervisor.

Safety infringement report.

Accident reporting.

Near miss reporting

Accident / Incident investigation report.

Safety target performance evaluation.

# ICSS Supplier Project Execution and Organisation

## ICSS Project Organisation

An efficient ICSS Supplier project organisation is important for successful execution of the project. The organization structure should be optimised to take into consideration the project size and nature, COMPANY and EPC Contractor requirements and the interaction with various parties.

Two categories of project organisation exist in IGFDP ICSS Supplier Projects; one for the ICSS Core Team (ICT) contracted by Company and the other being the ICSS Project Teams (IPT) contracted by EPC Contractor(s) or Group of EPC Contractors.

ICSS Supplier Project Teams (IPTs) 	Chapter 4.1.1 (By EPCs)

ICSS Supplier Core team (ICT) 	Chapter 4.1.2 (By Company)

### ICT roles

The ICT roles are essentially; monitoring and control across Projects, development of common standards (when used in more than one facility), testing of common standards, arbitration of standard deviations, overall QA coordination and audit, common usability/prototype testing, common compliance engineering. The ICT shall also have a secretary for administrative services, document controller (DC) to control the documents, an ICSS Quality Assurance (QA) Manager to monitor engineering quality, a Health Safety and Environment (HSE) officer and an ICSS designated local Cyber Security Officer (DLCSO).

### The IPT roles

The IPT roles are essentially; the execution the EPC Contractor’s ICSS contract, its project management,  procurement, building, drawing, documenting, testing, planning, invoicing, meeting with suppliers, site visits, visiting engineering house or sub-vendors, project QC. All project related testing is in the scope of work of each of the IPT. The IPT Project Manager heads his respective ICSS project team organisation.  He is responsible for the project implementation (Contracted by EPC Contractor).  He shall be supported by Lead engineer(s) and a team of engineers for hardware and software engineering work.  He and his project team shall interface with the ICT related to all technical matters on guidelines and standardisation.

From the ICSS tests or qualification phases (FIT, FAT , IFAT) ICSS Australian Engineers shall be planned as part on the ICSS development team for  the seamless transfer to ICSS Site, Operation phases and life cycle support.

The ICSS Supplier Information Technology (IT) engineer shall assist in setting up the IT infrastructure and necessary technical and office software support.

The ICSS Quality Manager shall be overseeing all ICSS Projects as common.

Refer to Attachment-01 for ICSS Project Organisation Chart.

### ICSS Supplier EPC Package PROJECT TEAM (IPT)

#### ICSS Supplier Project Manager (PM)

Prime point of contact for every aspect of the project on EPC Contractor basis.

Overall responsible for the project execution.

Overall responsible for the project deliverables as per EPC Package contract documents.

Responsible for issuing milestone invoices.

Interacts with the ICT.

Monitors and controls the project cost.

Responsible for change control.

Attends all project review meetings, e.g.  Basic Design Review (i.e. Hardware Freeze), Detail Design Review (i.e. Software Freeze) & System Readiness Review (SRR).

Responsible for resource management.

Responsible for hand over and project close out for EPC Package system

Overall responsible for the execution of the assigned EPC Package system

Overall responsible for the assigned EPC Package system as per contract.

Responsible for EPC Package related procurement.

Responsible for implementing engineering standardisation and quality within his project scope.

Responsible for sub-systems and interface with auxiliary systems within the scope for the assigned EPC Package.

Responsible for progress monitoring and reporting to ICT for the assigned project.

Responsible for cost control within the assigned EPC Package area.

Interacts with Project Engineering Manager for technical matters.

Provides progress feedback to ICSS Supplier Project Control Manager.

Report progress to EPC Package Contractor.

Responsible for conducting FAT for the assigned EPC Package system.

Responsible for conducting the IFAT

Responsible for the assigned plant system shipment.

Responsible for As-Built documentation after FAT for the assigned EPC Package.

Reports Project Director and copy to Engineering Manager and ICSS Supplier Project Control Manager.

#### ICSS Supplier Lead Project/System Integration Engineers (LPE/LSE)

Lead the hardware engineering teams

Responsible for developing FDS/DDS on Hardware

Responsible for co-ordination on PCS HW engineering including Console, Auxiliary Console, Marshalling Cabinet, System Cabinets, & Power Distribution Cabinet.

Responsible for IO signal assignment.

Perform Engineering Design Review for hardware and corresponding activities.

Responsible for developing plans and procedure for hardware testing.

Interact with alliance partners on technical issues.

Conduct Internal Test FIT, FAT and IFAT

Preparation of As-Built documentation after IFAT.

Report ICSS Supplier on project matters, also reports to Engineering Manager on technical matters; liaise with ICT Lead Hardware Engineers on technical matters.

#### ICSS Supplier Lead Software Engineers (LSE)

Leads the ICSS software engineering teams.

Responsible for developing FDS/DDS on Software (SW) & Human Machine Interface (HMI). [First lead software engineer assigned for the project only].

Develops typical control and logic schemes.

Perform Engineering Design Review for Software and corresponding activities.

Responsible for developing plans and procedure for software testing.

Responsible for PCS software engineering including sub-system.

Responsible for conducting PCS software internal testing.

Conduct Internal Test FIT, FAT and IFAT.

Reports to Project Manager on project matters, also reports to Engineering Manager on technical matters, liaises with ICT Lead Hardware Engineers on technical matters.

Liaise with Company Operation representatives for the HMI prototyping and standardisation.

#### Safety System Lead Engineer (FGS, SIS, HIPS)

Coordinate  the safety system vendor for safety system.(Principal Safety)

Interface with Vendor , participate to integration work and testing

Review Design Specifications.

Preparation of test procedures for prototyping.

Assures that all required drawings and documentation are produced by safety system vendors and as per project requirements.

Coordinates with Engineering Manager, System Integration Lead, Lead Hardware Engineer and Lead Software Engineer for respective plant technical issues.

Participates in technical meeting with PCS project team.

Support system integration and test of production.

Provides guidelines and assists Integration Lead Engineer.

Performs quality check for cabinet assembly work.

Prepares Specifications, documentation and related work.

Reports to Engineering Manager and System Lead Engineer.

#### ICSS Supplier 3rd Party Interface Engineer (SE)

Responsible and coordinate with all sub-system (UCP) vendors or 3rd party subsystems.

Liaises with Engineering Manager, System Integration Lead Engineer, Lead Project Engineer and Lead Software Engineer on all sub-systems related works.

Reports to ICSS Supplier Project Manager, Feedback to core team Safety System Lead Engineer.

Perform Subsystem Tests

#### ICSS Supplier QC Engineer (included in LPE and LSE roles)

Coordinates with QA Auditor for the quality control within the project and implementing project QA in line with company QA systems.

Conducts the Internal Quality check to ensure compliance with company QA requirements and PEP.

Coordinates with ICSS Supplier Project Manager for conducting engineering reviews.

Responsible for HSE implementation in the project office and staging area.

Lead & perform all System Tests

Provide quality input for pre-qualification of tenders

Review of tender documents and participation in tender clarifications

Responsible for coordinating all Quality Control inspections (including sub-supplier and sub-contractors).

Oversee package/contract MDR reviews

Arrange and/or attend Pre-Inspection Meetings with Contractors, Suppliers and Subcontractors

Ensure any Non Conformance Reports (NCRs) are distributed and closed out appropriately

#### ICSS Supplier Project/HW Engineers (PE)

Responsible for preparing the Overall System Architecture Drawing

Responsible for developing PCS Hardware FDS/DDS.

Responsible for developing detail panel drawings.

Responsible for developing detail console drawings.

Responsible for developing component numbering scheme.

Responsible for preparing buy out component specification.

Assists ICSS Supplier Lead Project Engineer and ICSS Supplier Lead Software Engineer in project implementation.

Preparation of tools and equipment for Internal Test, FAT and IFAT.

Reports to ICSS Supplier Lead Project Engineer

Perform System Tests

#### ICSS Supplier System/Software Engineers (SE)

Study Piping and Instrumentation Diagrams (P&IDs) and narratives

Responsible for developing PCS Software FDS/DDS.

Design, integrate and test Networks.

Carry out software generation and internal testing under guidance from the ICSS Supplier Lead Software Engineer.

Generate graphic pages based on graphic sketches.

Assist in conducting Internal Test, FAT and IFAT.

Provide site support when required.

Assist ICSS Supplier Lead Software Engineer in project implementation.

Report to ICSS Supplier Project Manager

Perform System Tests

#### ICSS Supplier Network & Security (NMS Eng.)

Responsible for developing Cyber security Procedure and Tools.

Design, integrate and test Networks.

Carry out NMS generation and internal testing under guidance from the ICSS Supplier Lead Software Engineer.

Assist in conducting NMS Internal Test, FAT and IFAT.

Provide site support when required.

Assist ICSS Supplier Lead Software Engineer in Cyber-security implementation.

Report to ICSS Supplier Project Manager all Cyber security issues

Perform NMS System Tests

#### ICSS Supplier CAD Technicians

Liaise with ICSS Supplier Lead Project Engineer on preparation, design, drafting of all the specific CAD drawings and indexes.

Ensure uniformity in term of CAD standards

Report to ICSS Supplier Lead Engineer

### ICSS Supplier (Yokogawa) Core Team (ICT)

The ICT is not EPC Contractor scope, ICT is directly contracted by Company

#### ICSS Supplier Project Director (PD)

Overall management responsible for the all IGFDP projects for ICSS.

Interface with COMPANY.

Appraises the Project sponsors and ICSS Supplier management.

ICSS PD shall interact with all ICSS PMs of individual EPC Contractors and also with Company for standardisation across all ICSS Projects.

#### ICSS Supplier Engineering Manager (EM)

Overall responsible for project engineering working closely with ICSS Supplier Project team and EPC Contractors.

Interface with COMPANY for standardisation across all ICSS Projects.

Overall responsible for developing project engineering specification

Overall responsible for engineering quality / standardisation / consistency

Responsible for technical correspondence with the ICT and project team.

Responsible for developing project engineering specification during the ICSS projects stages, if needed.

Organise and conduct review meetings with ICSS Supplier Project Managers and sub-vendor Project Managers.

Overall responsible for providing guidelines in conducting Internal Test and FAT.

Reports to ICSS Supplier Project Director.

#### YAU Coordinator (TM)

Responsible for total system integration.

Develops typical control and logic schemes.

Responsible for preparing sub-system communication specification

Responsible for Engineering Tool application.

Responsible for developing database exchange mechanism.

Guides the ICSS Supplier Lead Software Engineer in developing ICSS Configuration Design Document Specification for software.

Provides technical support in developing the Overall System Architecture.

Estimate system load.

Reviews the technical requirement of the various sub-systems.

Prepares specifications for sub-system communication.

Responsible for handling interface queries related to sub-system.

Coordinates with the ICSS Lead Software Engineer for detailed implementation of sub-system communication engineering.

Provides technical support in conducting prototyping, if necessary.

Reports to Engineering Manager

Coordinate Project/Technical matters with affiliates or Head Quarters.

#### SIS/FGS/AFS/HIPS Project Manager (HIMA PM)

Overall responsible for all Safety Systems project execution.

Interacts with the IPT Safety System teams.

Monitors and controls the HIMA project cost.

Responsible for safety change control.

Attends all project review meetings, e.g.  Basic Design Review (i.e. Hardware Freeze), Detail Design Review (i.e. Software Freeze) & System Readiness Review (SRR).

Responsible for resource management. Of safety teams

Responsible for hand over and project close out for EPC Package system

Overall responsible for the execution of the assigned EPC Package system

Overall responsible for the assigned EPC Package system as per contract.

Responsible for EPC Package safety related procurement.

Responsible for implementing engineering standardisation and quality within his project scope.

Responsible for sub-systems and interface with auxiliary systems within the scope for the assigned EPC Package.

Responsible for progress monitoring and reporting to ICT for the assigned project.

Responsible for cost control within the assigned EPC Package area.

Interacts with Project Engineering Manager for technical matters.

Provides progress feedback to ICSS Supplier Project Control Manager.

Report progress to EPC Package Contractor.

Responsible for conducting FAT for the assigned EPC Package system.

Responsible for conducting the IFAT

Responsible for the assigned plant system shipment.

Responsible for As-Built documentation after FAT for the assigned EPC Package.

Reports Project Director and copy to Engineering Manager and ICSS Supplier Project Control Manager.

#### ICSS Supplier System Integration Lead Eng. (SILE)

Leads the hardware engineering team (Principal Hardware)

Responsible for ICSS HW engineering compliance & consistency

Responsible for IO signal design.

Assists the Engineering Design Review

Responsible for developing plans and procedure for hardware prototyping test.

Interacts with sub-vendors on technical issues.

Provides guidelines and assists in conducting tests.

Provides guidelines in preparation of Specifications.

Reports to Engineering Manager on project and technical matters.

Liaise with Company representatives for the HW prototyping and standardisation.

#### ICSS Supplier Standard Application Team Leader (SATL)

Leads the PCS software engineering team. (Principal Software)

Responsible for developing Specifications on Software (SW) & Human Machine Interface (HMI).

Develops typical control and logic schemes (Standard Application Management).

Assists the Engineering Design Review.

Responsible for developing plans and procedure for software testing.

Responsible for PCS software engineering compliance & consistency including sub-system.

Responsible for conducting PCS software testing, SW and HMI design & prototyping tests.

Reports to Engineering Manager on project and technical matters.

Liaise with Company Operation representatives for the HMI prototyping and standardisation.

#### Safety System Team Leader (SSTL)

Review Design Safety Specifications.

Interface with Vendor , participate to integration work and testing

Preparation of prototyping test, and procedures.

Assures that all required drawings and documentation are produced to third part sub-systems’ and as per project requirements.

Coordinates with Engineering Manager, System Integration Lead, Lead Hardware Engineer and Lead Software Engineer for respective plant technical issues.

Participates in technical meeting with ICSS project team.

Reviews the technical requirement of the various Safety System.

Responsible for handling interface queries related to Safety Systems across projects.

Coordinates with the Project’s Safety Lead Software Engineer for detailed implementation of sub-system communication engineering.

Coordinates with Safety System vendor on Operation and/or Maintenance User Manuals.

Provides Safety System guidelines and assists in conducting tests, if necessary.

Prepares documentation and related Safety work.

Reports to ICSS Engineering Manager and Hima PM.

#### ICSS Supplier Solution Specialist (SOL)

Shared ICSS Supplier company services.

System/Solution specialist

Review of  specific specifications

Provides technical advice as required.

Visits site for resolving non PCS technical problems.

Reports to Project Director and Engineering Manager.

Coordinate Project/Technical matters with affiliates or Head Quarters Specialists

#### ICSS Supplier Project Control Manager (PCM)

Shared ICSS Supplier company services.

Monitors progress of overall projects.

Develops project review standard for review meetings

Reviews and Issues monthly progress report.

Provides guideline for issuing meeting notes and follow up on actions.

Monitors the issue of project purchase order.

Monitors delivery status of sub-vendor and free issue items from each EPC Contractor.

Responsible developing guidelines for Document control

Responsible for Expediting.

Invoicing.

Reports to ICSS Supplier Project Director and copy to Engineering Manager and liaises with all ICSS Supplier Project Managers.

#### ICSS Supplier Project Planner Engineer (part of PCM role)

Shared ICSS Supplier company services.

Develops and updates project Level 1 schedule.

Develops progress calculation method.

Computes monthly progress.

Prepares meeting notes.

Monitors document issue.

Prepares overall monthly report to COMPANY --and Not to EPC Contractor(s)--.

Reports to ICSS Supplier Project Control Manager and liaises with all ICSS Supplier Project Managers.

#### ICSS Supplier Document Controller(s) (DC)

Maintains record of all documents received and maintains a master copy.

Issues copies of documents received to ICSS Supplier Project Managers.

Maintains record of all documents issued to EPC Contractor(s).

Ensures copies of superseded drawings are stamped “SUPERSEDED” and filed separately.

Maintains a copy of all purchase orders issued.

Maintains status of document issue.

Maintains a copy of all commented documents.

Reports to ICSS Supplier Project Manager(s) and liaises with all EPC Contractor’s DC(s)

Reports to ICSS Supplier Project Control Manager and liaises with all ICSS Supplier Project Managers.

#### ICSS Supplier Project Support (PS)

Shared ICSS Supplier company services.

Responsible for all administration and related work.

Reports to Engineering Manager and liaises with all ICSS Supplier Project Managers.

#### ICSS Supplier QA Manager (QA)

Shared ICSS Supplier company services.

Responsible for implementing project QA in line with company QA systems.

Conducts the Internal Quality Audit to ensure compliance with company QA requirements and PEP.

Coordinates with Engineering Manager for conducting engineering reviews or 3rd party audits.

Responsible for HSE implementation in the project office and staging area.

Liaises with all Project Quality Control on quality related issues.

Co-ordinates and participates in Company QA audits in accordance with agreed schedule.

Ensure consistency of quality application throughout all work-fronts.

Ensure that quality records are being compiled and handed over in a consistent manner from all work-fronts.

# Communication Procedures

Communication protocol shall be agreed between EPC Contractor personnel and ICSS Supplier lead project engineer or ICSS Supplier lead system engineer for technical matters, however all communication shall be copied to the ICSS Supplier Project Manager.

For contractual issues related to this order, i.e.  Commercial and schedule commitments, confirmation of or deviations from the scope of supply, written authorisation by/to the ICSS Supplier Project Manager is required.

All communications by email are informal.

## Internal Project Meetings

An internal project weekly review meeting is to be carried out with the participation of all the ICSS Supplier project team members.

## Technical Meetings

Technical meetings shall be held in the presence of the ICSS Supplier Project Manager or his authorised delegate.

Minutes shall be made of all agreements/actions.

Minutes are considered to be invalid if they have not been approved (or undersigned if originated) by the ICSS Supplier Project Manager or his authorised delegate and other party.

The ICSS Supplier Project Manager shall notify EPC Contractor in writing, if he delegates his responsibility for any particular meeting.

Ad hoc Technical meeting could also be triggered by Eng. or Technical Manager

## Monthly Progress Meetings

Monthly Progress Meetings with COMPANY/EPC Contractor is to be held at ICSS Supplier (Singapore) or EPC Contractor Office, to be mutually agreed with EPC Contractor, with ICSS Supplier Project Manager and/or his authorised delegates with notification to COMPANY and attendance when deemed appropriate.

Minutes shall be made of all agreements/actions.

Minutes are considered to be invalid if they have not been approved (or undersigned if originated) by the ICSS Supplier Project Manager or his authorised delegate and a COMPANY representative.

The ICSS Supplier Project Manager shall notify the COMPANY/EPC Contractor in writing, if he delegates his responsibility for any particular meeting.

### Frequency/Location of Meetings

The frequency of meetings and the location of each meeting shall be mutually agreed between the ICSS Supplier and EPC Contractor.

Progress meeting shall be held at least once a month as minimum; frequency may vary upon Project phase or EPC Contractor request.

The regular uses of Video/Web Conference and/or Telephone Conference are encouraged.

Effort shall be made to minimise the number of meetings needed, combining both technical and management meetings and promoting good and focus agenda.

## ICSS Supplier Project Reviews, Basic Design Review (i.e. Hardware Freeze), Detail Design Review (i.e. Software Freeze) and System Readiness Review (SRR)

A periodic project review shall be internally carried out every Months.

A report to EPC Contractor shall be sent within two weeks of this project review stating the progress, which has been made.

All reviews shall be conducted in ICSS Supplier Singapore office.

### Basic Design Review milestone (HWF)

A basic design review meeting shall be carried out when the review on all FDS/DDS documents have been completed by EPC Contractor.  All materials shall be made available at least two weeks, (14 days) prior to the scheduled review for each work area. Duration is subject to specific EPC Contractor agreements, 14 days is the default duration as per Company requirement. FDS/DDS Documents shall be reviewed or approved throughout the “Specify Phase”.

HW Prototype/DVT review by Company

The HWF milestone shall have a QA audit including report of documents completeness.

### Detail Design Review milestone (SWF)

The detail design review meeting shall take place when the reviews on all FDS/DDS documents have been completed by EPC Contractor.  All materials shall be made available at least two weeks, (14 days) prior to the scheduled review for each work area. Duration is subject to specific EPC Contractor agreements, 14 days is the default duration as per Company requirement.

FDS/DDS Documents shall be reviewed or approved throughout the “Development Phase”.

SW Prototype review by Company Operation representative.

The SWF milestone shall have a QA audit including report of documents completeness.

### System Readiness Review milestone (SRR)

The SRR shall take place when all work activities have been completed and ICSS has fully completed the Internal Test.  All materials shall be made available at least three weeks, two weeks, (14 days) prior to the scheduled review for each work area. Duration is subject to specific EPC Contractor agreements, 14 days is the default duration as per Company requirement.

The SRR milestone shall have a QA audit including report of documents completeness.

### Review Cycle

The net review cycle shall be nominally 14 working days per document, also the same is to be agreed with EPC Contractor.

The net approval time is generally 14 working days, unless specified otherwise and agreed with EPC Contractor.

ICSS Supplier as well as EPC Contractor shall send approved and/or reviewed documents by the fastest possible means (in general by express courier or Electronic files on ICSS Supplier Project ftp Server)

Duration is subject to specific EPC Contractor agreements, 14 days is the default duration as per Company requirement.

# Procurement Management

## Responsibility

The ICSS Supplier Project Manager for each ICSS project shall be overall responsible for the procurement activity with consultation with ICT.

## Uniform Hardware

The hardware used throughout the all EPC Package should be of uniform type and make.  To ensure this, the ICSS Supplier shall prepare the hardware specifications with the help of project team in accordance with the project specifications of ICT.  The ICSS Supplier shall submit the specifications to the EPC Contractor for approval.  Upon approval the ICSS Supplier shall invite quotations from approved vendors.  After negotiation, ICSS Supplier shall prepare a list of final selected make and model number for each type of hardware.  ICSS Supplier shall issue this list to the EPC Contractor for approval.  Upon receiving approval, ICSS Supplier shall circulate the approved list to all members of the project teams, ICT and all vendors for compliance.

Procurement groups has pre-qualified supplier list and procedures, refer to ICSS Supplier work standards: SEW-F-601 Procurement of Non-Yokogawa Products SEW-F-603 3rd Party Vendor Classification and Criteria for Evaluation.

Procurement shall also be in accordance with the IGFDP ICSS approved Vendor List and their Classifications controlled by ICT. All IPT change management related to the approved ICSS Vendor, Supplier and Products list must be informed to the ICT and shall required COMPANY approval.

## ICSS Hardware

ICSS Supplier Project Manager, ICSS Supplier Project Control Manager & Engineering Manager (ICT) shall hold a meeting with the Yokogawa Asia Singapore Pte. Ltd. (YAS) Production Planning Department within two (2) months from the date of official order from the EPC Contractor and an ordering schedule shall be established for the initial order quantity.  The Production Planning Department shall also be informed of short notice requirement for certain type of hardware for contingency plan.  Individual ICSS Supplier Project Manager shall issue the actual order for their assigned plants.  Additional quantities as required shall be ordered based on the final input documents from the EPC Contractor.

## SIS/FGS/HIPS/AFS (HIMA)

The ICSS Supplier Project Manager shall be responsible for issue of LOI/PO, progress monitoring, and commercial issues.  ICSS Supplier Project Manager for the individual EPC Package shall handle all technical matters relating to their plant.  SIS vendor shall have a separate team for each plant similar to the PCS team and they shall interact for implementation and testing.

## Other Packages

Typically packages shall be defined by the EPC Contractor requirement to the ICSS Supplier, but not limited to.

The ICSS Supplier Project Manager shall be responsible for issue of LOI/PO, progress monitoring.  The ICSS Supplier Project Manager shall handle the commercial issues.

ICSS Supplier Project Engineering Manager shall coordinate all technical requirements with the OTHER PACKAGES.

## Expediting

The ICSS Supplier Project Manager and panel-manufacturing department (PMD) shall keep track of the delivery status of items ordered.  They shall inform the ICSS Supplier Project Control Manager if there is any delay.  The ICSS Supplier Project Control Manager shall follow up the vendor and visit vendor offices if required for expediting the items.

The ICSS Project Manager/Controller shall report to their respective EPC Contractor expediting in charge if any delay or logistic situations are occurring.

# Technical clarification

Technical clarifications are expected throughout the entire project phase.  In order to maintain a systematic way to manage the important technical related issues which do not have schedule or commercial impacts but requires clear direction, firm decision and prompt response, Technical Clarification Procedure shall be used to raise such issue.

Technical Clarification Notice is not intended as replacement of good communication, TCN shall be minimized according the importance of the clarifications and risks. Other standard route of communication such as technical discussions, meetings, emails are shall be preferred.

Hardware related Technical Clarification shall be avoided to be used after HWF milestone, suitably CRF shall be used.

Software related Technical Clarification shall be avoided to be used after SWF milestone, suitably CRF shall be used.

Technical Clarification Notice (TCN) is used by ICSS Supplier, following the Technical Clarification Procedure (TCP), to raise technical related issue to customer who must return with firm reply within 14 days which schedule delay and commercial impact are not anticipated.  However, delays in reply to Technical Clarification could result in project schedule delay or commercial impact. 
Duration subject to specific EPC Contractor agreements, 14 days is the default duration as per Company requirement.

Refer to Attachment-02: for ICSS Technical Clarification Procedure and Technical Clarification Notice.

## Technical Clarification Procedure

The clarifications could be initiated by either COMPANY/EPC Contractor or ICSS Supplier.

The Technical Clarification Procedure as per Attachment-02 in this document, details the responsibilities of involved parties and how the Technical Clarification Notice (TCN) is to be filled-in and submitted to EPC Contractor for approval via a Project transmittal.

The TCN clarifier shall respond to the TCN within 14 days of receipt (or longer according to its complexity) and sent the written TCN response to the ICSS Supplier. The ICSS Supplier shall verify the TCN’s impact assessment on ICSS and shall implement accordingly. Duration subject to specific EPC Contractor agreements, 14 days is the default duration as per Company requirement.

A log of Technical Clarification Notice shall be maintained by the ICSS Supplier Project Team (and no by the DCC).

# ICSS Change Management

Changes are inevitable in projects of this nature. Efficient change management shall control cost, schedule, impact, implementation and testing of the project changes.

## Change Request Procedure

The change can be initiated by either COMPANY/EPC Contractor or ICSS Supplier project team via Project transmittal or formal Project communication route with record of communications.

The Change Request Procedure as per Attachment-03 in this document, details the responsibilities of involved parties and how the Change Request Form (CRF) is to be filled-in and submitted to EPC Contractor for approval.

Refer to Attachment-03: for ICSS Change Request Procedure and Change Request Form.

The COMPANY/EPC Contractor must approve the change within fourteen (14) days of receipt and issue a written approval (together with the signed CRF) to ICSS Supplier, to ensure no further change in project schedule and cost impacts.  After receiving COMPANY/EPC Contractor’s approval, ICSS Supplier shall then implement the change(s).
Duration is subject to specific EPC Contractor agreements, 14 days is the default duration as per Company requirement.

Change(s) shall not be implemented for unapproved CRF.

CRF could be approved or rejected, and valid if approved before date.

Prices submitted shall be in accordance with Volume Discount Price Agreement (VDPA) pre-agreed between ICSS Supplier and COMPANY.

A log of Change Request form shall be maintained by the ICSS Supplier Project Team (and not by the DCC).  Categories such as hardware, software, documents others can be covered using this Change Request Form.

## Change Management Process

The change management process includes commercial meetings, submission of Change Order to EPC Contractor or COMPANY respectively, together with price breakdown quotation.

The change order form shall be the consolidation of all change requests (both CRF issued by ICSS Supplier and change notices issued by COMPANY/EPC Contractor) that have commercially impact ICSS Supplier on the implementation, execution and management of project.

It shall be initiated by ICSS Supplier project team via Project transmittal or formal Project communication route with record of communications.

The Change Order Procedure as per Attachment-08 in this document, details the responsibilities of involved parties and how the Change Order Forms (COFs) is to be filled-in and submitted to COMPANY/EPC Contractor for approval.

Refer to Attachment-08: for ICSS Change Order Procedure with Change Order Form.

### ICSS Change Order

Change Order form shall be sent to COMPANY/EPC Contractor who must approve the change within fourteen (14) days of receipt and issue an official purchase order to ICSS Supplier within two (2) weeks.
Duration is subject to specific EPC Contractor agreements, 14 days is the default duration as per Company requirement.

The variation order shall be reviewed and an acknowledgement shall be sent back to EPC Contractor.

A log of Change Orders for EPC Contractor shall be maintained by the ICSS Supplier Project team (and not the DCC)

Figure 8-1  Change Management Process

# Document Handling

The engineering work involves handling of documents which may undergo revisions and be subsequently re-issued.  Proper control of these documents is essential for efficiency, schedule and quality.  The following procedure is proposed to manage and control documents.

ICSS Vendor Document Control Procedure shall be in accordance with Company procedures Specification Contractor Document and Data Management Requirement C035-AG-SPC-0002.

## ICSS Supplier FEED/PRE-FID and Project Documents relationship

### ICSS Supplier FEED Documents Life Cycle (from FEED/PRE-FID till end of ICSS Projects)

During the FEED/PRE-FID period, Standard ICSS specifications are the common documents and standard specifications generated according to the COMPANY project specifications. FEED/PRE-FID documents shall be issued by ICT and accepted by COMPANY.  These documents shall be considered as ICSS Project standard documents and are to be used for all ICSS packages or EPC Vendor Packages interfacing with ICSS within the Ichthys Gas Field Development Project, to be adopted by each EPC Contractor. These documents shall be issued to each EPC Contractor by COMPANY.

These documents shall be used and updated throughout the life cycle of the entire Ichthys Gas Field Development Project.

Common practices (control schemes, signal flow diagram, hardware, general components, etc.), naming philosophy for document, equipments, instruments, devices, cables, etc., and solutions such as interface with other sub-systems, are determined by ICT team.  They are used by each ICSS project team for each EPC Contractor ICSS package.  However, they shall not to be reproduced or changed by each ICSS project team.  Therefore, any change to such requirements shall be maintained by ICSS Core Team (ICT).

### ICSS Supplier Project Documents Life-Cycle (by Each ICSS Project Team during EPC Contractor Project)

ICSS FEED documents are not meant to cover each ICSS project’s specific requirements which shall be issued by each EPC Contractor.  ICSS project team has to understand these documents generated during ICSS FEED and additionally generate project related and customised document(s) for the specific project.

Refer to chapter 9.4 describing the ICSS Project team document deliverables.

Figure 9-1	Typical ICSS Supplier Project Documentation Structure

## Document Server, Software Platform & Applications

Yokogawa Singapore has centralised project servers with enhanced security features for project use.  A specific folder has been created for IGFDP ICSS Project on this server.  Sub folders are created for various subjects within this main folder for project documents.  The server is maintained under ICSS Supplier IT including appropriate Disaster/Recovery and Offsite storage standard IT procedure.  This facility is used for internal filing and/or data exchange (SEW-EM-701 Software Backup and Disaster Recovery)

All engineers in the project are equipped with individual PC or notebook computer with access to the project server.  The ICSS Supplier Project Manager shall assign appropriate access right to each engineer in his assigned project.  All engineers and above shall have an individual Email account and Internet access.

Following are the ICSS Supplier office licensed software used (subject to change upon ICSS Supplier policy).

MS Windows XP Professional® or Vista Professional.

MS Project 2007 Professional®

MS Office 2007 Professional®

AutoCAD 2010®

Adobe Acrobat® 8.0 compatible

McAfee Virus Scan Enterprise® 8.0.0

## Document Controller

A document controller shall be assigned to manage the documents.  They shall:

Receive and maintain a master copy of all incoming documents.

Issue all incoming documents as per distribution list.

Notify periodically the project team the document status.

Maintain a master copy of all outgoing documents.

Keep track of document issue and approval status.

Issue and control the Outgoing Document transmittal.

Receive and control the incoming Document transmittal.

## ICSS Project Documents

Each EPC Contractor shall contract a list of ICSS Project document deliverables for each Project team according to the specific EPC Contractor scope and requirement.

These Project documents are often specified with “Generate” or “Provide” as per EPC Contractor requirement and shall be considered a project deliverables by each ICSS package (ICSS Supplier and its sub-Vendors).

The typical list of such ICSS Project document deliverables is indicated in Attachment-06, and shall be the minimum basis for each package (ICSS project document List), also timely document delivery  milestones (namely, HWF, SWF and SRR) is logically associated as per the ICSS Development Cycle requirement.

Different document categories (i.e. Functional Design, Detail Design, SRR, As Built) is considered by ICSS Supplier as a set of multiple document(s) required for a specific review phase, i.e. multiple documents may be generated for each category.

Refer to Attachment-06: for the standard EPC Contractor ICSS Project Document’s requirements (with standard ICSS Document Titles and Numbers).

ICSS Supplier and its sub-vendors shall issue the following sets of document deliverables:

Project/General Specifications

ICSS functional and design documents (newly created by the project team in accordance to FEED specifications, otherwise customised documents shall be generated wherever applicable.)

As-Shipped documents after FAT.

ICSS Standard Specifications are the reference such as control drawings; logic scheme (that shall be used for bulk generation), typical cabinet arrangement and wiring drawings were established with the maximum number of components that can be mounted. The ICSS FEED/PRE-FID typical drawings shall be used as template for individual ICSS Supplier Project’s cabinet drawings, based on actual number of components to be installed in a cabinet.

The actual project populated drawings shall be submitted for EPC Contractor’s approval

ICSS Supplier project and design documents are those that are approved by EPC Contractor for ICSS implementation. These documents shall be submitted on CD-ROM or hard copy for record and reference.  Manufacturing and FAT shall be based on effective (approved) design documents. Any changes to “approved design documents” shall involve rework and shall affect the delivery.

ICSS Supplier Project documents are classified into several categories beyond the document requirement as followed:

### ICSS Supplier Project control Documents (Internal)

ICSS Supplier Project control (Main PO , Contract…etc)

Communications (MoM, letters  ...etc)

PO/INVOICE/DO/DN

Shipping Doc

Etc...

### Inputs (from EPC Contractors)

Input data and documents and are logged in Master ICSS Supplier Project Inputs Document list.
EPC Contractor is responsible for timely supplying the functional definition or analysis for the facility to the ICSS Supplier.

This is a standard list but not limited to:

User requirements and standards

EPC Contractor Project Specification/Standards

EPC Contractor Project Requirement and milestones

P&ID/PFD/FLD/C&E/Logic Diagrams/Graphic sketches/Control and Logic Narratives

Equipment list and datasheets, Instrument list and datasheets

IO DBs (refer to chapter 2.3.2) as per the pre-agreed validated excel data format.
(IO DB quantity & quality assessment by IPT for each IODB1, 2 & 3 milestones)

SOPs (for OTS) supplied by EPC contractor and reviewed by Company.

3rd Party, P2, P3 Package information(s) as listed above.

The EPC Contractor to provide the schedule for each delivery of the above items to ICSS Suppliers.

Refer to Attachment-11: for the ICSS Input list requirements from EPC Contractor for the ICSS Development

### ICSS Supplier Project Deliverables (Contractual)

#### ICSS Supplier Project Planning

Done once at KOM and logged in Master Outgoing ICSS Supplier Project Doc List.

- KOM (MOM)

- PEP

- PQP

- System topology

#### ICSS Supplier Project Design/Specifications (HWF, SWF, SRR, As Shipped)

ICSS Documents are logged in the ICSS Supplier’s Master Outgoing Project Doc Register.

- Specification/Functional Design Specification (FDS)

- Detail Design (DDS)

- Construction Drawings

- Test plan and Test Procedures (does not required updates or re-submission once effective and executed)

#### Test Reports/Records/Results

ICSS Documents are logged in Master Outgoing ICSS Supplier’s Project Doc Register, originals to be records delivered to EPC Contractor.

#### Vendor Manuals

Generally regulated by copyright or Licenses, not duplicable and original.

- ICSS Supplier Instruction/Operation/Maintenance Manuals

- Product Manuals/Datasheets

- Vendor Manuals

- Licenses

Please note that specifically for the above items unauthorised copies or duplications is fraudulent and shall not be carried out by ICSS Project even though wrongly or contractually specified by EPC Contractor as document deliverables.

## Document Approval

All documents issued for the first time for review or approval by EPC Contractor shall be reviewed or approved within 14 days of submission. Documents that are revised and resubmitted for approval shall be returned approved or with further comments within 14 days. (Or to be agreed in accordance with EPC Contractor Project specifications, 14 by default unless specified)

The comments may be listed separately or marked on the electronic document proper or on a print to enable revision. (Or to be agreed in accordance with EPC Contractor Project specifications)

Following colours code shall be used while commenting on the print documents or spreadsheets:

Track changes feature may be used when commenting on electronic version of MS Word or Excel documents.

If Adobe Acrobat format is used for documents, spreadsheet and drawings, changes should be colour-coded as the above-mentioned or using Acrobat Notes.

If colour-coded remarked is not convenient, cloud marks (function in Acrobat) shall be used.

However, in additional to colour-coded remarks, cloud marks can still be used concurrently for easy identification of comments.

## Document Format

ICSS Supplier document format shall be delivered as per COMPANY Document format requirement:

MS Office 2003 Professional suits compatible for all text documents, tabular documents, charts, database, block diagram, sketch, organisation chart, scheduling.

Adobe Acrobat 8 for documents sent, and for review.

AutoCAD 2003 Compatible for drawings.

No password is allowed on project generated document e-files

## Document Structure

### Document edited using MS Office

All documents shall have a cover page and contents page. The cover page shall show the project name, the document title, the document number and the revision status.  All pages shall have same consistent revision number.  The document file number including file revision shall be shown on the bottom left hand side.  Page number and total pages shall be shown on the bottom right hand side.

Native document may have a different files as such the child document shall trace the same document no and revision no of parent document.

Modification of a document’s shall automatically induce the document to be revised and reflect changes in the revision history.

Final document deliverable submitted to EPC Contractor/COMPANY DC shall be one (pdf) document/file.

Primary Company Document no. shall be shown associated secondary ICSS Supplier Document No. 
Example: C810-AJ-PLN-0001 (IGFDP-C0-PC-00-0100-001); PEP

### AutoCAD Drawings

All AutoCAD drawings, except overall system architecture drawings, shall be A3/A4 size.  Overall system architecture drawings could be A1 or A0 size if necessary.  All A3/A4 size drawings shall have an A4 cover page.  All pages shall have a title block.  The revision number for all pages shall be same.  The file number shall be shown at the bottom left hand side of the drawing.

## Document Numbering Philosophy

For ICSS Supplier document numbering philosophy, please refer to attachment within this document for details.

COMPANY Document no. shall apply (Controlled By Company), dual numbers can be used, and Company document no. shall be the master including cross reference.

Refer to Attachment-04: for ICSS Document Numbering Philosophy (ICSS and PCS Document Title and Number).

Document control and secondary numbering shall followed ICSS Supplier Engineering standards governed by ICSS Supplier company policies and within ICSS Supplier audited compliance with ISO Standards as such the ICSS Supplier Project Document Control and Numbering shall comply with ICSS Supplier standard. EPC Contractor document control and numbering shall not remove or delete the initial ICSS Supplier documents reference and COMPANY Document requirement.

This rule shall be enforced wherever late or specific contractual EPC Contractor requirement interfered with Company or ICSS Supplier Documentation policies.

For EPC Contractor specific and related Document Control and Numbering information, as request by EPC contractor, shall be only additionally informed on a dedicated EPC Contractor dedicated coversheet placed on top of ICSS Supplier ICSS Documents.

No alterations of the native ICSS Supplier Document’s template are possible. (i.e. additions of Boxes, EPC Contractor text, Symbols, logos...etc)

For document revision procedure shall explain as in 9.10 below on Revision Control.

## EPC Phase Standard Document Requirements (ICSS and PCS Document Title and Number)

For ICSS Supplier Project document please refer to attachment within this document for details.

Refer to Attachment-06: for ICSS Supplier Project Document requirements (ICSS and COMPANY Document Title and Number).

### ICSS Native Document File Name

Company Document no. shall be shown associated to ICSS Supplier Document No.  
Example: C810-AJ-PLN-0001 (IGFDP-C0-PC-00-0100-001); PEP

The native file name is the ICSS Supplier document number (strictly) and followed by revision number which shall be explained below.  The file extension is the native file format.

For example the native file number for this document is IGFDP-C0-PC-00-0100-001_rev00.doc.

If the document has an “attachment” the file numbering shall be the document number followed by “-01”, followed by a revision number.  The “-01” implies the first attachment.

For example, native file number for this document with one attachment shall be IGFDP-C0-PC-00-0100-001-01.rev00.doc.  The extension number shall be the corresponding native file format extension.

If the file is too big or document is breakdown, it could be divided into parts by adding “.01”, “.02”… etc.

All attachments, such as tables (spreadsheet), document files shall all trace to the parent’s file name

(See Figure 9-2  Document and Attachments native files Naming Convention-).

Figure 9-2  Document and Attachments native files Naming Convention

Example of one main native document with two attachments of which one contains two documents, and the other one with two attachment , i.e. first attachment with 1 spreadsheet , second attachment with 3 drawings:

Document native file name followed ICSS Supplier Engineering standards governed by Company policies and within ICSS Supplier audited compliance with ISO Standards as such the ICSS Supplier Project Document native file name shall solely comply with ICSS Supplier Project standard. EPC Contractor or external document native file naming shall not apply or nor interfere within ICSS Supplier Documents file naming standards.

This rule shall be enforced wherever late or specific contractual EPC Contractor’s requirement interfered with ICSS Supplier Documentation policies.

DCC shall reject any illegal document name, file name or revision deviating from the ICSS Project standard.

Company e-file name (pdf) sent to Company DC shall use Company Document no and revision no including COMAPNY effective cover page, as agreed with COMPANY.

Example Company e-file: C810-AJ-PLN-0001_A

### AutoCAD Documents

The native file numbering for AutoCAD drawings is drawing number followed by sheet number, followed by revision number. The file extension is the native file format.  SHT is abbreviation for sheet and NN is the sheet number. For example IGFDP-C0-00-PC-00-6000-001_SHT12_rev00.dwg

The native revision number is the revision number of that sheet.  All sheets must be issued every time any sheet is revised.

Company e-file name (pdf) sent to COMPANY DC shall use Company Document no and revision no including COMAPNY effective cover page, as agreed with COMPANY.

Example Company e-file: C810-AJ-PLN-0001_A

## Revision Control

Two revision controls applied for IGFDP

COMPANY Rev Control and shall follow COMPANY Document Procedure.

ICSS Supplier Company internal revision control

For the COMPANY Revision procedure refer to COMPANY Doc. Procedure C045-AG-PRC-0001.

The next section focuses only ICSS Supplier internal revision control; two levels of document revisions shall be used in the projects:

### Non-Effective specifications/Documents

For document revision, each document shall be saved as revision “D0” following by subsequent revision “D1”, “D2”, “D3” etc. sequentially.

Any documents under revision “Dn” are considered “Not effective” and are used to collect, from EPC Contractor’s feedback, comments, review, and suggestion etc. prior to issue of official documents.  They can be revised and re-submitted with a higher revision number after receiving comments from EPC Contractor.  However, if no comments, feedback, suggestions etc. are received from EPC Contractor within 15 days, the document could be resubmitted with an incremented revision No.

### Effective specifications/Documents

A revision “00” shall be used on documents that are considered “OFFICIAL” shall be sent for EPC Contractor’s official approval.  It can be subsequently revised to “01”, “02” etc.  All documents used from HWF onwards shall have minimum revision “00” till final “As-Built”.

Changes on effective documents (from Rev 00) shall only be done via an approved CRF/TCN.

Any changes on effective documents (from Rev 00) shall trace to a CRF/TCN/SLF, and CRF/TCN/SLF No shall be referred in its document revision history.

“As-Shipped” shall be printed on the documents which shall be lastly submitted in proper ICSS Supplier binders.  If required, all As-Built documents could be reset to revision “00” or other upon COMPANY Doc requirement; however this is not ICSS Supplier default practice.

Documents marked with “For Information” are used to communicate with EPC Contractor on information and knowledge.  They can be vendor’s product specification, manufacturers’ standard, product manual/instruction and documents generated to communicate information etc.

### Marking

The latest revision shall be highlighted in Word and Excel documents.  Cloud marking shall be made around the changes in the AutoCAD drawings for the latest changes only.  Cloud markings of all previous changes shall be de facto removed.

## Review on Engineering Document

All engineering and manufacturing documents generated by ICSS Supplier shall compulsorily undergo an internal project review prior its publication to COMPANY/EPC Contractor or any Implementation/manufacturing groups.

Evidence of review must be kept and files by the project team with the reviewer’s initial and date as minimum. Reviews evidence could be scanned to portal document format and stored in the project file server under specific project control directory, alternative they are filed.

ICSS Supplier Company internal revision control shall include the internal revision evidence of peer review (D0 for Internal review, D1 review results amended ...etc, etc) prior to first submission to COMPANY/EPC Contractor (RevA)

Internal ISO audit is to be carried out to verify compliance to documentation procedure requirement.

COMPANY Quality or IM group may conduct periodic review or external audit where applicable.

Document audited found with obvious lack of review or quality is a serious company threat and/or engineering risk, Project non conformances shall be duly raised by QC auditor to QA department for relevant corrective and Preventive Actions.

## As-Shipped Documents

As-Shipped documents are prepared after the final acceptance of the Integrated IFAT by the COMPANY and EPC Contractor.  These shall be submitted earliest one month from the date of FOB.  The documents are issued in CD-ROM and a minimum of one copy in print and/or according the EPC Contractor ICSS Project contractual requirement.

## Update of Document at EPC Contractor’s Plant Site

All changes/modifications at EPC Contractor Plant Site are under EPC Contractor Site controlled change procedure/work permit procedure and are EPC Contractor Site responsibility.

The procedure of updating documents at site shall be in accordance with the EPC Contractor Project Specification for Site Work.

The ICSS Contactor Project Change Control procedure (TCN, CRF, SLF...etc, etc) shall be followed if no procedure are in place or effective by the Site EPC Contractor.

Changes during installation and site commissioning often take place also the EPC Contractor/ICSS Supplier change control procedure shall includes as minimum:

All changes made during the site installation and commissioning activity are marked up on a Master Document print.

EPC Contractor representative at site shall sign the site marked up copy, according to EPC Contractor Change control procedures.

A photocopy of the marked documents is kept at site for reference and the original copy is taken to the regional or site office for updating and issue revised As-Built documents, with an update revision.

Updated As-Built documents are issued in CD-ROM and one (or more) copy in print minimum or as per COMPANY/EPC Contractor “As Built” deliverable requirement.

After the ICSS validation (IFAT) the ICSS is under formal configuration Management.  All ICSS change shall be control by a System Log Form

Refer to Attachment-07: for System Log Form requirements

# Correspondence

All formal incoming correspondences (to ICSS Supplier) related to documentation are to be addressed to the ICSS Supplier Project manager. The nominated representative must sign incoming correspondence.

Outgoing correspondence is to be addressed to the nominated representative.

The ICSS Supplier Project Manager or ICSS Supplier Lead project/system engineer shall sign outgoing correspondence.

## Correspondence References

### ICSS Supplier External correspondence

#### Outgoing Correspondence to Clients

Outgoing correspondence shall be sequentially numbered for unique identification, in an 18-digit format with groups of strings and numbers separated by hyphens “-“:

| A | A | A | A | A | - | B | B | B | - | C | C | - | D | - | N | N | N |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

A total of 18-digit of combined characters and numbers are used for correspondence numbering.

Where:

| A | A | A | A | A | : | The first 5-character string “AAAAA” denotes the acronym for the project. |
| --- | --- | --- | --- | --- | --- | --- |
| I | G | F | D | P | - | Ichthys Gas Field Development Project. |

| B | B | B | : | The first 3-character string “AAA” denotes the acronym for sender. |
| --- | --- | --- | --- | --- |
| Y | E | A | - | Yokogawa Engineering Asia Pte. Ltd. |

| C | C | : | The second 2-character string “BB” denotes the acronym for receiver, i.e. ICSS’ Client for the End-User’s project. These 2 character can be any one of the following number or character (0~9, A~Z). |
| --- | --- | --- | --- |
| C | O | - | COMPANY or ICSS Core Team Common files |
| C | L |  | COMPANY or ICSS Core Team Onshore files (common) |
| C | A |  | COMPANY or ICSS Core Team Offshore files (common) |
| G | N |  | General Use |
| L | N |  | EPC for Onshore LNG Plant package (LNG) by JKC |
| L | U |  | EPC for Onshore Package (jetty , Off-site , Utility) by JKC |
| L | C |  | EPC for Onshore Package (CCPP) by CCPP EPC Contractor |
| B | T |  | EPC for Offshore CPF Top Side package by? |
| B | H |  | EPC for Offshore CPF Hull package by? |
| B | S |  | EPC for Offshore CPF SPS package by |
| S | T |  | EPC for Offshore FPSO Top Side package by? |
| S | H |  | EPC for Offshore FPSO Hull package by? |
| S | R |  | EPC for Offshore FPSO Turret package by SBM |

| D | : | The 1-character string “C” denotes the acronym for type of correspondence categories. |
| --- | --- | --- |
| C | - | Commercial |
| E | - | Engineering |
| F | - | Fax |
| L | - | Letter |
| M | - | Minutes Of Meeting |
| R | - | Report |

| N | N | N | : | The last 3-digit number “NNN” is used sequentially for each type of outgoing-to-Client correspondence categories. |
| --- | --- | --- | --- | --- |
| 0 | 0 | 1 |  | 001~999 are to be used for each outgoing-to-Client category. |
| ~ |  |  |  |  |
| 9 | 9 | 9 |  |  |

e.g.  IGFDP-YEA-CO-M-001

(A minute of meeting sent from ICSS Supplier to COMPANY.)

The Document Controller shall file all original outgoing correspondence and a log is maintained.

#### Outgoing Correspondence to Sub-Vendors

Should an internal meeting, discussion, or review be recorded, a reference number shall be used to identify it with sequentially numbered for unique identification, in a 13-digit format with groups of strings and numbers separated by hyphens “-“:

| A | A | A | A | A | - | B | B | B | - | N | N | N |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 3 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

A total of 13-digit of combined characters and numbers are used for correspondence numbering.

Where:

| A | A | A | A | A | : | The first 5-character string “AAAAA” denotes the acronym for the project. |
| --- | --- | --- | --- | --- | --- | --- |
| I | G | F | D | P | - | Ichthys Gas Field Development Project. |

| B | B | B | : | The second 3-character string “BBB” denotes the acronym for receiver, i.e. Sub-Vendor |
| --- | --- | --- | --- | --- |
| S | B | V | - | Sub-Vendor of ICSS Supplier for Ichthys Gas Field Development Project |

| N | N | N | : | The last 3-digit number “NNN” is used sequentially for each type of outgoing to sub-vendor correspondence. |
| --- | --- | --- | --- | --- |
| 0 | 0 | 1 |  | 001~999 are to be used for each outgoing to sub-vendor. |
| ~ |  |  |  |  |
| 9 | 9 | 9 |  |  |

e.g.  IGFDP-SBV-001

(A reference number for correspondence has been sent from ICSS Supplier to sub-vendor.)

This reference number is created together with the following fields, i.e. Date; Serial Number; Revision Mark; Sub-Vendor’s company name; Category; Type, Purpose; Originator’s name; involved Project and Remarks.

The Document Controller shall file all original outgoing correspondence and a log is maintained.

#### Incoming Correspondence

All official incoming correspondence shall also be track in the similar manner if not controlled by EPC Contractor correspondence procedure requirement. (Or to be agreed according to EPC Contractor Project specifications).

| A | A | A | A | A | - | B | B | - | C | C | C | - | D | - | N | N | N |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |

A total of 18-digit of combined characters and numbers are used for incoming correspondence numbering.

Where:

| A | A | A | A | A | : | The first 5-character string “AAAAA” denotes the acronym for the project. |
| --- | --- | --- | --- | --- | --- | --- |
| I | G | F | D | P | - | Ichthys Gas Field Development Project. |

| B | B | : | The first 2-character string “AA” denotes the acronym for receiver, i.e. ICSS’ Client for the End-User’s project. These 2 character can be any one of the following number or character (0~9, A~Z). |
| --- | --- | --- | --- |
| C | O | - | COMPANY or ICSS Core Team Common files |
| C | L |  | COMPANY or ICSS Core Team Onshore files (common) |
| C | A |  | COMPANY or ICSS Core Team Offshore files (common) |
| G | N |  | General Use |
| L | N |  | EPC for Onshore LNG Plant package (LNG) by JKC |
| L | U |  | EPC for Onshore Package (jetty , Off-site , Utility) by JKC |
| L | C |  | EPC for Onshore Package (CCPP) by CCPP EPC Contractor |
| B | T |  | EPC for Offshore CPF Top Side package by? |
| B | H |  | EPC for Offshore CPF Hull package by? |
| B | S |  | EPC for Offshore CPF SPS package by |
| S | T |  | EPC for Offshore FPSO Top Side package by? |
| S | H |  | EPC for Offshore FPSO Hull package by? |
| S | R |  | EPC for Offshore FPSO Turret package by SBM |

| C | C | C | : | The second 3-character string “BBB” denotes the acronym for sender. |
| --- | --- | --- | --- | --- |
| Y | E | A | - | Yokogawa Engineering Asia Pte. Ltd. |

| D | : | The 1-character string “C” denotes the acronym for type of correspondence categories. |
| --- | --- | --- |
| C | - | Commercial |
| E | - | Engineering |
| F | - | Fax |
| L | - | Letter |
| M | - | Minutes Of Meeting |
| R | - | Report |

| N | N | N | N | : | The last 4-digit number “NNNN” is used sequentially for each type of incoming-from-Client correspondence categories. |
| --- | --- | --- | --- | --- | --- |
| 0 | 0 | 0 | 1 |  | 0001~9999 are to be used sequentially for each official correspondence sent from Client to ICSS Supplier. |
| ~ |  |  |  |  |  |
| 0 | 9 | 9 | 9 |  |  |

e.g.  IGFDP-CO-GN-YEA-M-001

The Document Controller shall file all original incoming correspondence and a log shall be maintained.

### Internal Correspondence (Within ICSS Supplier)

Outgoing correspondence to ICSS sub-vendors shall be sequentially numbered for unique identification, in a 12-digit format with groups of strings and numbers separated by hyphens “-“:

| A | A | A | A | A | - | B | B | B | - | N | N | N |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 0 | 1 | 2 | 3 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

A total of 13-digit of combined characters and numbers are used for correspondence numbering.

Where:

| A | A | A | A | A | : | The first 5-character string “AAAAA” denotes the acronym for the project. |
| --- | --- | --- | --- | --- | --- | --- |
| I | G | F | D | P | - | Ichthys Gas Field Development Project. |

| B | B | B | : | The second 3-character string “BBB” denotes the acronym for receiver, i.e. Sub-Vendor |
| --- | --- | --- | --- | --- |
| Y | E | A | - | ICSS Supplier internally |

| N | N | N | : | The last 4-digit number “NNNN” is used sequentially for each type of outgoing to sub-vendor correspondence. |
| --- | --- | --- | --- | --- |
| 0 | 0 | 1 |  | 001~999 are to be used for each outgoing to sub-vendor. |
| ~ |  |  |  |  |
| 9 | 9 | 9 |  |  |

e.g.  IGFDP-YEA-001

(A reference for correspondence has been generated within ICSS Supplier Ichthys Gas Field Development Project Team.)

This reference number is created together with the following fields, i.e. Date; Serial Number; Revision Mark; Category; Type, Purpose of Correspondence; Originator’s name; involved Project and Remarks.

The Document Controller shall file all internal correspondence and a log is maintained.

# ICSS Supplier Project Document Templates

## The project document templates

The project document templates shall be used throughout the project cycle.  The templates for documents are as per Attachment-05.

Refer to Attachment-05: for ICSS Project Document Template and the attachment template.

## EPC Contractor/Company coversheet

The COMPANY/EPC Contractor Coversheet templates shall be used throughout the project cycle (refer to Chapter 9.8).  The templates for documents are as per Attachment-11.

Refer to Attachment-11: for the ICSS Project Document Cover page template to be amended for each EPC Contractor during EPC phase.

# Disaster Recovery

The purpose of this section describes the steps used to recover from disaster and maintain progress and manage adverse impact on ICSS Supplier Distributed Control System and ICSS Supplier Projects.

This applies to projects with complex software configurations or contractual disaster recovery requirements.

Disaster is defined as any event that renders an ICSS Supplier facility implementing a project unusable.

The Disaster Recover Procedures are governed by ICSS Supplier Company Operation policies. (SEW-EM-701 Software Backup and Disaster Recovery)

## Recovery Responsibilities

It is the responsibility of the ICSS Supplier Project Manager or designee to ensure that the requirements of this procedure are instituted on applicable project.

## Recovery Overview

ICSS Supplier operates Engineering facilities in geographically diverse areas across the Asia Pacific regions, which provide alternate sites and staff for implementation of projects.  In addition, ICSS Supplier systems manufacturing facilities are located in Singapore, backed up by Yokogawa's Manufacturing facilities in Japan.  ICSS Supplier's practice is to prepare all project documentation, including drawings, specifications and software development on computers and to "back-up" on appropriate storage media with offsite storage.

## Recovery Procedure

### Hardware and System Software Back-up

ICSS Supplier systems are primarily centred on hardware and system software products of Yokogawa Electric Corporation that has facilities producing hardware and software systems in Japan and Singapore.  In the event of a disaster at an ICSS Supplier facility, these resources would be utilised to repair/replace lost and damaged products and to mitigate impact to the projects.

### Inventory for Hardware and System Software at Back-up Locations

System hardware and system software shall be drawn from ICSS Supplier Inventory Equipment in any location, Singapore Manufacturing Inventory, Yokogawa Headquarters Inventory in that order.  No specific back-up hardware shall be maintained.

### Application Software Back-up

Each project shall have back-up media containing the current software development.  The disaster management/recovery process includes the generation of the back-up copies of the software development.  Two media sets shall be used in rotation for daily backup of the project.  An additional back up shall be made weekly and stored in an off-site location.

The effectiveness of the regular ICSS Supplier Project Back Up on alternative tapes shall be duly audited by the Technical/Engineering managers (log of back/up with date, name and Initial).

Failure to observe this standard operating policy shall be considered a serious Company threat, the auditor shall duly raised the CAR to the relevant authorities to enforce the policies with CA/PA.

### Documentation Back-up

Each project shall establish and maintain accurate backup electronic media for ICSS Supplier generated project documentation.  Backup media shall include formal customer inputs, submittals, drawings and specifications.  The back-up shall be held in an off-site storage location on weekly basis to provide replacement in the event of loss of the original file.

The LAN Administrator backs up the information stored on the project directory in the server.  No project involvement is required for this data.

### Recovery

In the event of disaster recovery, the ICSS Supplier Project Manager shall recover the back-up software, assemble the project team, locate/order replacement hardware and carry on the project.

Refer to ICSS Company work standards SEW-EM-701	Software Backup and Disaster Recovery Procedure